Obligation Work Plan of WV NSP Subrecipients

Objectives and Instructions

The goal of the Obligation Work Plan is to provide a clear path for each subrecipient to:

- achieve obligation as provided by the Subrecipient Contract by July 31, 2010;

- maintain compliance with NSP regulations;

- lay the foundation for additional activities that may be needed in order for the projects to be successful.

In addition to the critical information regarding the obligation requirement, the subrecipient will attach the following documents:

- Development budget – expenses; sources and uses

- Rental Budget – 10 year operating budget projections

- Homeownership Budget – include process/protocol for determining sales price; cost for counseling

- Program Delivery costs Budget through March 4, 2013

- Any other relevant project documents

This work plan will be developed in partnership with the subrecipient/developer and Cloudburst.  The subrecipient will be responsible for providing information about its project and draft the plan based on the template below.

Obligation Work Plan

May __ to July 31, 2010

| Project: | Subrecipient: |
| --- | --- |
| Total NSP Funds for Project: | Subrecipient Address: |
| Total # of units: |  |
| Main Contact: | Other Contacts: |
| Phone: | Phone: |
| Email: | Email: |

- Define Obligation for this project:

Funds are used when they are obligated by a state, unit of general local government, or any subrecipient thereof, for a specific NSP activity. Funds are obligated for an activity when orders are placed, contracts are awarded, services are received and similar transactions have occurred that require payment by the state, unit of general local government, or subrecipient during the same or a future period." (Federal Register, volume 73, N0. 194, p. 58332, October 6, 2008)

Obligation Breakdown – For all projects

| Activity | Amount | Date Obligation will be Fully Achieved | Notes |
| --- | --- | --- | --- |
| Acquisition |  |  |  |
| Financing |  |  |  |
| Rehab/Construction |  |  |  |
| Program Delivery Costs |  |  |  |
| Other |  |  |  |
| Total Project Cost |  |  |  |

- 25% Set-Aside

| Number of Units Meeting 25% Set-Aside |  |  |
| --- | --- | --- |
|  | Addresses of Properties Meeting Requirement |  |
| Total Projected Development Costs for 25% Set-Aside Units |  |  |
| Percentage of Total Project Costs |  |  |

To count towards required 25% at 50% of AMI set aside, property must be:

- Abandoned or foreclosed residential structure for rehabilitation/reconstruction

- Foreclosed residential vacant land for redevelopment

- Critical Path Schedule (CPS):

This spreadsheet will calculate your total project timeline for each property.  Fill out a separate spreadsheet for each property/activity you are conducting for NSP.  A sample CPS is provided in Exhibit A.

Instructions:

To access the spreadsheet, double click anywhere on it

Enter all days as CALENDAR DAYS

Items in Bold must be completed by the subrecipient

| Project Identification | Enter all pertinent information in header including: property address, total project funds, and CPS start date. Once the CPS is complete, use the spreadsheet to determine the projected obligation date. |
| --- | --- |
| Task Number: | Task numbers to identify each task listed. |
| Description of Task: | Enter sequentially each task needed to complete your project. |
| Days to Complete Task | Enter the number of calendar days expected to complete each individual task. |
| Days overlapping with already listed task | Enter the number of calendar days the task will run concurrently with a task PREVIOUSLY listed on the table. For example, your environmental review and historical review each take 30 days and will be conducted concurrently. In this schedule you list environmental review first and historical review second. For historical review, you would write 30 for “days overlapping with already listed task.” |
| Total Number of Days on Schedule | This column will auto-populate and will show the elapsed time since the start date of the Critical Path Schedule |
| Task Completion Date | This column will auto-populate and will show the expected completion date of each task with respect for prior tasks. |
| Estimated Amount of Funds Obligated | Enter the amount of funds that will be obligated upon the completion of the corresponding task. |
| Total Funds Obligated to Date | This column will auto-populate and will show the total obligation sum allowing you to easily calculate your expected date of “full obligation.” |
| TA Needed | List any TA needed to help you achieve the corresponding task. |

Below is a list of SOME of the tasks you should include in your Critical Path Schedule:

To Achieve Full Obligation

  - Identifying NSP compliant property

  - Signed Contract

  - Appraisal

  - Historical Review

  - Environmental Review

  - Property Closing

  - Environmental Remediation

  - Lead Based Paint Inspection

  - Lead Based Paint Abatement

  - Drawings and Specifications Completion

  - Inspections

  - Contract Bid

  - Contract Award Date

  - Homeowner Counseling

To Achieve Full Project Expenditure and Compliance

- Construction Begin

- Construction Completion

- Occupancy Certificate Achieved

- Rental Program

  - Marketing

  - Applications Accepted

  - Sign Lease

- Homeowner Program

  - Counseling

  - Marketing

  - Application

  - Closing with Homebuyer

- Monitoring and Reporting

Critical Path Schedule

- WV NSP Program Requirements and Rules

List Areas Where Project is not in Compliance WV NSP Policies and Procedures according to the WV NSP Policies and Procedures Manual:

| Area | Corrective Action | TA Needed |
| --- | --- | --- |

Funding Disbursement

Given the new procedures and forms, list the immediate steps that the subrecipient/for-profit developer needs to take in order to obligate properties and draw down funds.

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |
| 4. |  |

- Potential Obstacles to Achieving Obligation – List those not addressed elsewhere in the obligation plan.

| Obstacle | Steps to Overcome Obstacle (what, who, and by when) | TA Needed |
| --- | --- | --- |

- WVDO/WVHDF/Cloudburst will do the following to help the subrecipient achieve obligation.

WVDO will provide:

WVHDF will provide:

Cloudburst will provide:

- Signatures

Subrecipient 										Date

WVDO											Date

WVHDF										Date

Cloudburst										Date

Exhibit A – Sample Critical Path Schedule