## PUBLIC SERVICES
Community Development Block Grant COVID (CDBG-CV) Project Implementation Guide
WHAT? | WHO? | HOW?
TASK | Responsible Organization/Person | Applicable Documents/Resources/Comments
PROGRAM SET-UP
Applications Due
Application Review and Scoring | WVDO
Recommendations due for Awardees | WVDO
Governor Letter Announces Awards, Receipt of Letter sent to Subrecipient | WVDO | This letter notifies the local government that an application has been approved for funding. It also establishes the exact date from which costs may be incurred for the project. DO NOT PROCEED until you have been contacted by a WVDO representative.
Execution of State/Local Grant Agreement | Subrecipient/Admin | Evidentiary Checklist and Documents:
1. The Grant Agreement is the formal acceptance of the grant offer, including the terms and conditions involved. Once the agreement has been signed, it must be returned in 30 DAYS of reciept to the WVDO for further processing. A copy will be returned to the recipient for its files. |  | Grant Letter
Subrecipient Agreement
Legally Binding Agreement between Subrecipient and Non-Profit, Project Administrator, and/or Sub-Awardee
Program Specific CDBG-CV Policies and Procedures with required information
Grant Award Notice
Attachment A, Form C1- Budget
Attachment B, Form C2- Project Schedule
Attachment C, Form C3- Duplication of Benefits
Attachment D, Form C4- Environmental Review
Attachment E, Form C5- Grantee Debarment Form (SAMS.gov)
CV Program Policies and Procedures for Specific Program |  | Subrecipients are welcome to use WVDO's CV Policies and Procedures, revised to fit the Subrecipient's program. The following requirements must be included and should be followed in detail with the WVDO's CV Policies and Procedures:
a. Who can apply for Assistance and Applicant Eligibility (must be LMI and in Subrecipient's service area)
b. Supporting Documentation for Applicant Eligibility
c. How the Subrecipient will manage the Application Process
d. DOB Information and Required Documentation
e. COVID Tie Back Documentation and eligible claims for how a family describes COVID-19 impact.
f. Applicant Appeal Process
g. Applicant Confidentiality with the Subrecipient
h. Limited English Proficiency (LEP), Americans with Disabilities Act (ADA), Anti-Displacement and Relocation, and Fair Housing Act needs addressed
2. Place signed Grant Agreement and Evidentiary Materials in Agreement section of the file. | WVDO/Subrecipient/Admin
Schedule Implementation Meetings | WVDO Schedules | MEETING AGENDA:
Implementation Meetings are to provide a short session of Technical Assistance for the subrecipient. WVDO will provide TA for project administration and management procedures. WVDO will also answer any questions regarding the CDBG-CV Policies and Procedures and/or Grant Conditions. |  | Review Evidentiary Materials
Review Subrecipient Agreement (if returned before meeting)
Required Forms: Administrative and Program Forms
| WVDO/Subrecipient/Admin Attends | Review CDBG-CV Policies and Procedures
Payment Process
Project File Requirements
Approval of Program Documents | Subrecipient/Admin | Subrecipient Program Forms
All Subrecipient Program Forms need to be created by the Subrecipient and Approved by WVDO. |  | Tenant Application Form Homeowner Application Form Utility Assistance Application Form Landlord Certification Form Mortgage Lender Certification Form Marketing Materials for Advertisements (Flyers, Newspaper Ads, etc.) DOB-Self Certification Form (provided by WVDO)
Administrative Forms are provided by WVDO to follow Administrative Program procedures. | WVDO | Administrative Forms
Subrecipient Agreement Evidentiary Materials List and Forms Payment Request Form Quarterly Reporting Form Final Payment Form Close Out Report
Establish Project File
Includes- where applicable: | Subrecipient/Admin
1. Project Application, and Attachments: |  | 1. As submitted, including all amendment updates.
a. Budget & Duplication of Benefits
b. ACS/Census Beneficiary Analysis Source Documentation
c. HUD LMISD Source Documentation
d. Citizen Participation Plan and Supporting Documentation
e. Fair Housing Plan
f. Section 3 Plan
g. Assurances
h. Disclosure/Update Reports
i. Authorization and Certifications Form
j. Resolution Authorizing Filing of the Application
k. SAMS.gov Registration Page
l. Signed and Dated Copy of Cost Estimates from Local Government or Engineer
m. Other Funding Sources Commitment Letters
n. Clearly Defined Project Area Maps
topographical, aerial, and driving maps
o. Maps Clearly Relecting Census Area and Data
applies if the data is based on Census Tract Info. The Census area must coincide with the project area.
p. Census/Survey
q. Audit
ADDITIONAL DOCUMENTS REQUIRED IF COLLABORATING WITH A NON-PROFIT:
r. Verification of Partner Agency's 501( c )3 Status
s. Partner Agency Organizational Chart |  | s. This is to show how the proposed program fits into the overal organizational structure; include program staff or position
t. Most Recent Independent Auditors Report and Findings |  | t. Audit for Partner Agency, or if an Audit is not available, the most recent 990 Financial Statement
2. Subrecipient Agreement
3. Evidentiary Materials |  | 3. Materials in Checklist sent with Subrecipient Agreement
4. Program Forms with Policies and Procedures |  | 4. See above list of Administrative and Subrecipient Program Forms
5. General Correspondence
6. Payment Requests
7. Beneficiary Documentation (Applicant Information, Eligibility, and Requirements) |  | 7. Mortgage, Utility, and Rental Documentation Requirements found on pages 13-22 of CDBG-CV Policies and Procedures
9. State Monitoring/Inspection
10. Project Closeout
Establish a Financial Management System
Please note: numbers 6,7,9, and 10 do NOT need to be forms provided to WVDO; although, these processes must be included in the Subrecipient's CDBG-CV Program Policies and Procedures submitted with all Subrecipient Program Documents
1. Designate an individual responsible for financial management. | Subrecipient/Admin | 1. CDBG Manual, Chapter 3: Financial Management, A-87
2. Establish a non-interest bearing checking account for the receipt and expenditures of CDBG-CV funds. |  | 2. CDBG Manual, Chapter 3: Financial Management Cash Depositories. Funds granted to county commissions must be deposited in a non-interest bearing checking account.
3. Governing Body may wish to designate another individual to sign on behalf of the elected official when necessary. |  | 3. Such Individuals name and title must be included in the Letter of Transmittal accompanying the first Request for funds.
4. Establish bookkeeping procedures including the following document |  | 4. CDBG Manual, Chapter 3: Financial Management, pages 1-6. Atachment 3-1 and 24 CFR 85.
a. Cash Receipts Jounral |  | a. Recommended
b. Cash Disbursements Journal |  | b. Recommended
c. General Ledger |  | c. Recommended
d. Cash Control Register |  | d. If multiple Federal funding sources are used.
5. Adopt timesheet and time distribution forms, and instruct project staff as to their proper use. |  | 5. CDBG Manual, Chapter 3: Financial Management
6. Establish a written procedure for determing the reasonableness, allowability, and allocability of project costs, including the designation of an individual to review vouchers and invoices. |  | 6. CDBG Manual, Chapter 3: Financial Management. Documented in WRITING who will be responsible and how she/he will account for expenditures. Chief Elected Official and administrator must annotate each invoice.
7. Develop a written mechanism for ensuring compliance with the "three-day rule". |  | 7. Three Day Rule information is found in the CDBG Manual, Chapter 3, 3-3.
8. The responsible individual(s) should familarize themselves with drawdown procedures. |  | 8. CDBG Manual, Chapter 3: Financial Management
9. Establish travel regulation; cannot exceed state regulations. |  | 9. CDBG Manual, Chapter 3: Financial Management
10. Program Income Recording and Reporting. |  | 10. Chapter 4: Program Income, State/Local Contract Paragraph 6.
WVDO Issues Letter of Notice to Proceed with Categorically Excluded/Exempt Activities for Project | WVDO
Submit Monthly Reimbursement Requests to WVDO | Subrecipient/Admin | Subrecipient will use the Payment Request Form, the Invoive Summary Spreadsheet, and provide all supporting documentation and invoices where applicable. Please note: PII should not be included in any spreadsheet and must never be sent over email.
Advertisements of Program Application Availability | Subrecipient/Admin
Emergency Payments Begin | Subrecipient/Admin
Reporting Requirements | Subrecipient/Admin
The Subrecipient must provide WVDO with quarterly reports and a close-out report. These reports must include the status and progress of the expenditure of funds under the Subrecipient Agreement, in addition to any other information requested by WVDO. | Subrecipient/Admin | 1. Quarterly reports are due to WVDO no later than 15 days after the end of each quarter of the program year and must be sent each quarter until submission of the administrative close-out report. The ending dates for each quarter of the program year are March 31, June 30, September 30, and December 31. The first quarterly report due pursuant to this agreement is due for the quarter ending June 30, 2020.
2. The close-out report is due thirty (30) days after termination the Subrecipient Agreement or 30 days after completion of the activities contained in the Subrecipient Agreement, whichever occurs first.
Final Payment Request to WVDO (with all Accomplishment Dates)/ Emergency Payments Complete | Subrecipient/Admin
Monitoring | WVDO
Checks WV State Auditors Office for Last Audit | WVDO
Closeout Project | WVDO

## PUBLIC FACILITIES
Community Development Block Grant COVID (CDBG-CV) Project Implementation Guide
WHAT? | WHO? | HOW?
TASK | Responsible Organization/Person | Applicable Documents/Resources/Comments
PROGRAM SET-UP
Applications Due
Application Review and Scoring | WVDO
Recommendations due for Awardees | WVDO
Governor Letter Announces Awards, Receipt of Letter sent to Subrecipient | WVDO | This letter notifies the local government that an application has been approved for funding. It also establishes the exact date from which costs may be incurred for the project. DO NOT PROCEED until you have been contacted by a WVDO representative.
Execution of State/Local Grant Agreement | Subrecipient/Admin | Evidentiary Checklist and Documents:
1. The Grant Agreement is the formal acceptance of the grant offer, including the terms and conditions involved. Once the agreement has been signed, it must be returned in 30 DAYS of reciept to the WVDO for further processing. A copy will be returned to the recipient for its files. |  | Grant Letter
Subrecipient Agreement
Legally Binding Agreement between Subrecipient and Non-Profit, Project Administrator, and/or Sub-Awardee
Program Specific CDBG-CV Policies and Procedures with required information
Grant Award Notice
Attachment A, Form C1- Budget
Attachment B, Form C2- Project Schedule
Attachment C, Form C3- Duplication of Benefits
Attachment D, Form C4- Environmental Review
Attachment E, Form C5- Grantee Debarment Form (SAMS.gov)
CV Program Policies and Procedures for Specific Program |  | Subrecipients are welcome to use WVDO's CV Policies and Procedures, revised to fit the Subrecipient's program. The following requirements must be included and should be followed in detail with the WVDO's CV Policies and Procedures:
a. Who can apply for Assistance and Applicant Eligibility (must be LMI and in Subrecipient's service area)
b. Supporting Documentation for Applicant Eligibility
c. How the Subrecipient will manage the Application Process
d. DOB Information and Required Documentation
e. COVID Tie Back Documentation and eligible claims for how a family describes COVID-19 impact.
f. Applicant Appeal Process
g. Applicant Confidentiality with the Subrecipient
h. Limited English Proficiency (LEP), Americans with Disabilities Act (ADA), Anti-Displacement and Relocation, and Fair Housing Act needs addressed
2. Place signed Grant Agreement and Evidentiary Materials in Agreement section of the file. | WVDO/Subrecipient/Admin
Schedule Implementation Meetings | WVDO Schedules | MEETING AGENDA:
Implementation Meetings are to provide a short session of Technical Assistance for the subrecipient. WVDO will provide TA for project administration and management procedures. WVDO will also answer any questions regarding the CDBG-CV Policies and Procedures and/or Grant Conditions. |  | Review Evidentiary Materials
Review Subrecipient Agreement (if returned before meeting)
Required Forms: Administrative and Program Forms
| WVDO/Subrecipient/Admin Attends | Review CDBG-CV Policies and Procedures
Payment Process
Project File Requirements
Approval of Program Documents | Subrecipient/Admin | Subrecipient Program Forms
All Subrecipient Program Forms need to be created by the Subrecipient and Approved by WVDO. |  | Tenant Application Form Homeowner Application Form Utility Assistance Application Form Landlord Certification Form Mortgage Lender Certification Form Marketing Materials for Advertisements (Flyers, Newspaper Ads, etc.) DOB-Self Certification Form (provided by WVDO)
Administrative Forms are provided by WVDO to follow Administrative Program procedures. | WVDO | Administrative Forms
Subrecipient Agreement Evidentiary Materials List and Forms Payment Request Form Quarterly Reporting Form Final Payment Form Close Out Report
Establish Project File
Includes- where applicable: | Subrecipient/Admin
1. Project Application, and Attachments: |  | 1. As submitted, including all amendment updates.
a. Budget & Duplication of Benefits
b. ACS/Census Beneficiary Analysis Source Documentation
c. HUD LMISD Source Documentation
d. Citizen Participation Plan and Supporting Documentation
e. Fair Housing Plan
f. Section 3 Plan
g. Assurances
h. Disclosure/Update Reports
i. Authorization and Certifications Form
j. Resolution Authorizing Filing of the Application
k. SAMS.gov Registration Page
l. Signed and Dated Copy of Cost Estimates from Local Government or Engineer
m. Other Funding Sources Commitment Letters
n. Clearly Defined Project Area Maps
topographical, aerial, and driving maps
o. Maps Clearly Relecting Census Area and Data
applies if the data is based on Census Tract Info. The Census area must coincide with the project area.
p. Census/Survey
q. Audit
ADDITIONAL DOCUMENTS REQUIRED IF COLLABORATING WITH A NON-PROFIT:
r. Verification of Partner Agency's 501( c )3 Status
s. Partner Agency Organizational Chart |  | s. This is to show how the proposed program fits into the overal organizational structure; include program staff or position
t. Most Recent Independent Auditors Report and Findings |  | t. Audit for Partner Agency, or if an Audit is not available, the most recent 990 Financial Statement
2. Subrecipient Agreement
3. Evidentiary Materials |  | 3. Materials in Checklist sent with Subrecipient Agreement
4. Program Forms with Policies and Procedures |  | 4. See above list of Administrative and Subrecipient Program Forms
5. General Correspondence
6. Payment Requests
7. Beneficiary Documentation (Applicant Information, Eligibility, and Requirements) |  | 7. Mortgage, Utility, and Rental Documentation Requirements found on pages 13-22 of CDBG-CV Policies and Procedures
9. State Monitoring/Inspection
10. Project Closeout
Establish a Financial Management System
Please note: numbers 6,7,9, and 10 do NOT need to be forms provided to WVDO; although, these processes must be included in the Subrecipient's CDBG-CV Program Policies and Procedures submitted with all Subrecipient Program Documents
1. Designate an individual responsible for financial management. | Subrecipient/Admin | 1. CDBG Manual, Chapter 3: Financial Management, A-87
2. Establish a non-interest bearing checking account for the receipt and expenditures of CDBG-CV funds. |  | 2. CDBG Manual, Chapter 3: Financial Management Cash Depositories. Funds granted to county commissions must be deposited in a non-interest bearing checking account.
3. Governing Body may wish to designate another individual to sign on behalf of the elected official when necessary. |  | 3. Such Individuals name and title must be included in the Letter of Transmittal accompanying the first Request for funds.
4. Establish bookkeeping procedures including the following document |  | 4. CDBG Manual, Chapter 3: Financial Management, pages 1-6. Atachment 3-1 and 24 CFR 85.
a. Cash Receipts Jounral |  | a. Recommended
b. Cash Disbursements Journal |  | b. Recommended
c. General Ledger |  | c. Recommended
d. Cash Control Register |  | d. If multiple Federal funding sources are used.
5. Adopt timesheet and time distribution forms, and instruct project staff as to their proper use. |  | 5. CDBG Manual, Chapter 3: Financial Management
6. Establish a written procedure for determing the reasonableness, allowability, and allocability of project costs, including the designation of an individual to review vouchers and invoices. |  | 6. CDBG Manual, Chapter 3: Financial Management. Documented in WRITING who will be responsible and how she/he will account for expenditures. Chief Elected Official and administrator must annotate each invoice.
7. Develop a written mechanism for ensuring compliance with the "three-day rule". |  | 7. Three Day Rule information is found in the CDBG Manual, Chapter 3, 3-3.
8. The responsible individual(s) should familarize themselves with drawdown procedures. |  | 8. CDBG Manual, Chapter 3: Financial Management
9. Establish travel regulation; cannot exceed state regulations. |  | 9. CDBG Manual, Chapter 3: Financial Management
10. Program Income Recording and Reporting. |  | 10. Chapter 4: Program Income, State/Local Contract Paragraph 6.
Authorization to Use Grant Funds | WVDO
Issue Letter of Notice to Proceed with Categorically Excluded/Exempt Activities for Project. | WVDO
Subrecipient Submits Monthly Draw for Admin | Subrecipient/Admin
Advertisements of Program Application Availability | Subrecipient/Admin
Emergency Payments Begin | Subrecipient/Admin
Reporting Requirements | Subrecipient/Admin
The Subrecipient must provide WVDO with quarterly reports and a close-out report. These reports must include the status and progress of the expenditure of funds under the Subrecipient Agreement, in addition to any other information requested by WVDO. | Subrecipient/Admin | 1. Quarterly reports are due to WVDO no later than 15 days after the end of each quarter of the program year and must be sent each quarter until submission of the administrative close-out report. The ending dates for each quarter of the program year are March 31, June 30, September 30, and December 31. The first quarterly report due pursuant to this agreement is due for the quarter ending June 30, 2020.
| Subrecipient/Admin | 2. The close-out report is due thirty (30) days after termination of this Agreement or 30 days after completion of the activities contained in this Agreement, whichever occurs first.
Submit Reimbursement Requests to WVDO | Subrecipient/Admin | Subrecipient will use the Payment Request Form, the Invoive Summary Spreadsheet, and provide all supporting documentation and invoices where applicable. Please note: PII should not be included in any spreadsheet and must never be sent over email.
Final Payment Request to WVDO (with all Accomplishment Dates)/ Emergency Payments Complete | Subrecipient/Admin
Monitoring | WVDO
Checks WV State Auditors Office for Last Audit | WVDO
Closeout Project | WVDO